Project management - an overview

Project plan and schedule - example

Information A project plan is a detailed schedule or timeline showing: all the tasks that need to be completed who will be doing those tasks key dates or milestones for phased delivery and final completion of the project The plan should show not only the full timetable from start to completion but also the interdependencies between tasks or resources - what has to happen by when and what must be done before the next set of tasks can be started, etc. You can use a computer program to produce a project plan and this is often particularly useful for complex or multi-strand projects. On simpler projects you can use whatever suits the way you work and the type of project you're doing. Often a calendar, spreadsheet or simple flow diagram will be enough. In this example we present a project for a business to relocate to new premises, showing some of the main elements involved, how they overlap or depend on other elements and how this can be represented on a simple plan to show who is doing what at the various stages from start to completion. To limit the extent of the project for the purposes of this example, we've assumed that the new premises have been purpose built and some tasks that relate to occupying a new building are deliberately omitted here, such as testing heating and hot water systems, air conditioning, etc. We've also assumed that electrical, telecoms and IT cabling installation has been done as part of the build. It is important to note that all projects are different and require different amounts of detail according to their complexity. Many formal project management processes were originally developed for use with very large and multi-strand projects such as those in construction and technology. Always limit your documentation and management to a level that's appropriate for your particular project. Example document begins on next page

Project plan and schedule

Relocation to new premises

Stage 1 - planning process

This shows an approach to the considerations needed in planning this relocation. Filling in the task column has also prompted additional tasks that need to be done first.

Dates - deadlines or milestones and end date

The lease on existing premises expires on Friday 30 July - must have relocated and cleared/cleaned premises by this date. Lease on new premises commences Monday 28 June. IT contractor requires 5 working days to install and check computer systems.

Tasks - what needs to be done / who by

General administration and preparation before move

| Task | Responsible | Other considerations |
| --- | --- | --- |
| Get estimates for various components of the move. | Office |  |
| Arrange all necessary insurances for new premises. | Office |  |
| Set up accounts for utilities. | Office |  |
| Set up new telecoms/internet/account. | Office / IT |  |
| Order new stationery. | Office |  |
| Notify existing customers and suppliers of move and change of address. | Office / sales & marketing |  |
| Update website with new address and contact details. | Office / sales & marketing / IT |  |
| Layout plan (eg equipment, stock, seating, etc). | Office |  |
| Book mail redirection. | Office |  |
| Create new H&S induction to reflect new premises. | Office |  |
| Create fire plan, decide on assembly points, etc. | Office | Speak to Fire Service |
| Arrange sandwich delivery, etc. | Office |  |
| Existing premises |
| Deliver storage crates. | Storage co | Place order for these |
| Pack personal effects, desk contents, etc. | Staff | Allow time to sort / dispose of anything not needed - files, redundant or outdated material, etc *Get shredder sacks |
| Deliver recycling containers for paper, card, etc. | Waste co | Place order for these |
| Deliver skips for large/bulky waste. | Skip co | Place order for these |
| Furniture/equipment/machinery/computers to be disassembled. | Removal co / IT |  |
| Pack stock, etc. | Removal co |  |
| Deliver equipment/machinery/computers to new premises. | Removal co | Obtain quotes, choose and book removal co |
| Deliver stock to new premises. | Removal co | Book removal co |
| Skips to be removed. | Skip co |  |
| Clean building. | Cleaning co | Book this |
| New premises |
| Building fit-out |  |  |
| Fit flooring. | Carpet co | Select and order |
| Unpack / install furniture, equipment, machinery, computers, etc. | Removal co / IT contractor | Date? |
| Deliver new furniture/equipment/computers. | Equipment co | Select and order these - delivery date? |
| Test computer network. | IT contractor | Allow 1 day + day contingency |
| Install and test telephone system. | Telecoms co | Book telecoms co |
| Install exterior signage. | Sign co | Design, place order and book installers |
| Unpack stock, etc. | Removal co / staff |  |
| Unpack personal effects, desk contents, etc. | Staff | Report any faults with phones, computers, equipment, etc ASAP |
| Snagging - building, equipment, IT, phones, etc. |  | From 30 July onwards |

Project plan as a Gantt chart